## Evangelization Framework
The Church in DSJ must move from a "maintenance" mode to a "mission" mode for greater growth.
Mission | Form disciples of Jesus Christ. Change the world. Inspire others to do the same.
Goals | Double the # of disciples in five years. Each disciple to positively change four lives per year.
| WORD |  | WORSHIP | WITNESS
Critical | Faith programs ineffective in forming |  | The average parionshioner's liturgical | Catholics consumed by daily routine;
Issue | personal relationships with Jesus Christ |  | experience considered "average" at best. | Unwilling to help those most in need.
Key | Huge decline in youth formation > 1st HC |  | Only 16% attend Mass weekly | > 10% living below poverty levels
Data | Parents' faith not properly formed |  | > 50% attending less than "fully engaged" | Stewardship of time (< 25% volunteer)
Points | Adults uncertain about a personal God |  | Aging parishes; young adults missing | Stewardship of treasure (< 1% of income)
| Quality / quantity of FF programs |  | Homilies - disconnected; uninspiring | Lack of awareness on key social issues
Root | Faith formation does not respond to |  | Music - not uplifting or engaging | Parishes not invested in social ministry
Causes | contemporary or secular culture |  | Hospitaility - not welcoming | Few encounter opportunities
| Parionshioners not inspired to attend |  | Generational issues | Few personal invitations to help
Pillar | Develop deep, personal |  | Make Sunday Liturgy the highlight | All parishioners to encounter Jesus
Mission | relationships with Jesus Christ |  | of people's week | Christ by serving those in need
Suggested | High quality / quantity of FF programs |  | More inspiring homilies | High quality / quantity of encounter opps
Goals | High quality / quantity of FF leaders |  | Higher quality, uplifting music | Increase parishioner participation in service
| Strengthen personal prayer life for all |  | Parishioners actively engaged in Liturgy | Increase financial stewardship
| Faith Formation Strategy and Plan |  | Strong Liturgy Director / Committee | SM Committee | Clergy Leadership
Possible | Strong FF Director | Engaged Clergy | Professional homily coaching / feedback | Stewardship Plan | SM education
Actions | Relevant programs | Skilled Leaders | Skilled musicians and music leadership | Create encounters | Personal invitations
| Marketing | Satisfaction rating | "Active engagement" training / feedback | Satisfaction rating | Share testimonials

## Word Plan
Pillar Mission: To form deep, personal relationships with Jesus Christ
MACRO STEP(S) | 1. Develop a highly effective Faith Formation leadership team; | 3 | Establish a process to solicit feedback for each
| 2. Develop a comprehensive Faith Formation plan; |  | Faith Formation program / event.
GOAL
50% of parishioners praying 10+ minutes per day by 12/16; 70% by 12/17; 90% by 12/19
Program | Key Actions |  | Comments
| Develop: a plan to assess / strengthen the prayer lives of all parishioners |  | Informal assessment as to where people are at
Strengthen | Communicate: expectations for / benefits of daily prayer |  | Need a formal communication plan for this
Personal | Develop: teach people how to pray |  | Thru homilies, bulletin, classes, etc.
Prayer Lives | Enable: make it easy for people to pray with books, websites |  | Consider sharing testimonials of +++ parishioners
| Monitor: Solicit feedback from each FF program. |  | Update "prayer life" rating at least annually
GOAL
Achieve an average rating of 8+ for all programs by June 2017; rating of 9 by June 2019.
Program | Key Actions |  | Comments
| Assess: the effectiveness and reach of current FF programs / events. |  | See sample matrix
Increase # of Quality | Scope: Identify programs to ensure there is something for all parishioners |  | Faith communities; retreats, speaker series, etc.
Programs and | Communicate: to parishioners the goal to "Invest in Their Faith" |  | Need a very strong communication plan
Attendance | Personally invite parishioners to participate in 1 FF event per quarter. |  | Set your own goals for participation
| Monitor: Solicit feedback from each FF program. |  | Need a formal evaluation process and tool.
GOAL
Achieve a 50% increase in the # of quality FF leaders (8+ rating) by 6/17; 100% increase by 6/19
Program | Key Actions |  | Comments
| Assess: the role and effectiveness of each current FF leader |  | Need some estimated starting point
Increase the # of | Develop: a recruitment and development plan to add skilled FF leaders. |  | Consider goals, roles, funding and measures.
High Quality | Communicate: expectation that all adults and parents are FF leaders |  | FF leaders not limited to "instructors"
FF Leaders | Develop: provide FF leaders and parents with proper training. |  | Classes, online tools, etc.
| Assess: Solicit feedback on FF leaders; train / coach as needed |  | Back into roles and goals.
Notes: | Each "Key Action" will need a more detailed "program" with specifc steps. |  | Note: All SMART goals listed are for
| Action Plans would typically be prepared by the person "Responsible" |  | illustrative purposes. Each parish to set
| for the execution of the plan. Each action plan could have its own RACI. |  | their own specific SMART goals.

## Word RACI
|  |  | R | Responsible for execution.
Pillar Mission: Develop Deep Personal Relationships with Jesus Christ |  |  | A | Accountable that action gets completed
|  |  | C | Consultation required before execution
|  |  | I | Inform, but advance approval not required.
Targeted
Strengthen Prayer Lives | Start | End | RACI CHART
Key Actions | Date | Date | A | B | C | D | PC | FC | DSJ
Develop: a plan to assess / strengthen the prayer lives of all parishioners
Communicate: expectations for / benefits of daily prayer
Develop: teach people how to pray
Enable: make it easy for people to pray with books, websites
Monitor: Solicit feedback from each FF program.
Increase the # of Quality FF Programs | Start Date: Start; End Date: End; RACI CHART A: RACI CHART
Key Actions | Date | Date | A | B | C | D | PC | FC | DSJ
Assess: the effectiveness and reach of current FF programs / events.
Scope: Identify programs to ensure there is something for all parishioners
Communicate: to parishioners the goal to "Invest in Their Faith"
Personally invite parishioners to participate in 1 FF event per quarter.
Monitor: Solicit feedback from each FF program.
Increase the # of Quality FF Leaders | Start Date: Start; End Date: End; RACI CHART A: RACI CHART
Key Actions | Date | Date | A | B | C | D | PC | FC | DSJ
Assess: the role and effectiveness of each current FF leader
Develop: a recruitment and development plan to add skilled FF leaders.
Communicate: expectation that all adults and parents are FF leaders
Develop: provide FF leaders and parents with proper training.
Assess: Solicit feedback on FF leaders; train / coach as needed
Dates and responsibilities to be determined by each parish.
| PC | Pastoral Council (Parish Council)
| FC | Finance Committee
| DSJ | Chancery (will need to be more specific based on needs)

## Worship Plan
Pillar Mission: To Make Sunday Liturgy THE Highlight of People's Week
MACRO STEP(S) | 1. Develop a strong Liturgy team / committee. | 3 | Establish a process whereby parishioners can
| 2. Document a detailed plan on how to improve Sunday Liturgy |  | routinely provide feedback on the Liturgy.
GOAL
Improve average homily rating by 1 point each of next 3 years; average of 8.5+ by 2020
Program | Key Steps |  | Comments
| Establish / share homily standards |  | DSJ level activity
Improve | Develop: clergy training, videotaping, coaching, peer review |  | DSJ to provide ncessary funding (???)
Homilies | Communicate: share homily standards and goals with parishioners |  | Make parishioners an important part of process
| Understand parishioners' needs / issues. Allocate proper prep time. |  | Consider a parish team to assist with messaging
| Solicit feedback weekly; monitor satisfaction rating semi-annually. |  | Formal, visible feedback mechanism.
GOAL
Improve average music rating by 1 point each of next 3 years; average rating of 8.5 by 2020
Program | Key Steps |  | Comments
| Secure / hire a strong director of music; establish a music board. |  | Consider a shared resource if cost is an issue.
Improve | Document a music improvement plan. Consider parishioner input. |  | Resources; training; environment, goals; funding
Music | Communicate: share music plans and goals with parishioners |  | Help parishioners understand standards.
| Develop: choirs, musicians, and parishioners. |  | Recorded songs on website to assist parishioners
| Solicit feedback weekly; monitor satisfaction rating semi-annually. |  | Formal, visible feedback mechanism.
GOAL
Improve ave. participation rating by 1 point each of next 3 years; average rating of 7.5 by 2020
Program | Key Steps |  | Comments
| Develop and share a plan to increase full, active , conscious participation |  | Formal communication plan required.
Increase Full | Establish / share the elements of FACP (full active conscious participation) |  | Suggest 10 distinct and objective elements
Active, Conscious | Develop: educate parishioners on Liturgy and participation elements |  | Parishioners self-assess where they are curretly at
Participation | Enable: create an environment conducive to FACP |  | Environment includes supportive ministers
| Remind parioshioners; solicit feedback; monitor rating annually. |  | Visible feedback; share testimonials.
Notes: | Each "Key Action" will need a detailed "action plan" with specifc steps. |  | Note: All SMART goals listed are for
| Action Plans would typically be prepared by the person "Responsible" |  | illustrative purposes. Each parish to set
| for the execution of the plan. Each action plan could have its own RACI. |  | their own specific SMART goals.

## Worship RACI
|  |  | R | Responsible for execution.
Pillar Mission: Make Sundat Liturgy THE highlight of people's week. |  |  | A | Accountable that action gets completed
|  |  | C | Consultation required before execution
|  |  | I | Inform, but advance approval not required.
Targeted
Improve Homilies | Start | End | RACI CHART
Key Steps | Date | Date | A | B | C | D | PC | FC | DSJ
Establish / share homily standards
Develop: clergy training, videotaping, coaching, peer review
Communicate: share homily standards and goals with parishioners
Understand parishioners' needs / issues. Allocate proper prep time.
Solicit feedback weekly; monitor satisfaction rating semi-annually.
Improve Music | Start Date: Start; End Date: End; RACI CHART A: RACI CHART
Key Steps | Date | Date | A | B | C | D | PC | FC | DSJ
Secure / hire a strong director of music; establish a music board.
Document a music improvement plan. Consider parishioner input.
Communicate: share music plans and goals with parishioners
Develop: choirs, musicians, and parishioners.
Solicit feedback weekly; monitor satisfaction rating semi-annually.
Increase Full, Active, Conscious Participation (FACP) | Start Date: Start; End Date: End; RACI CHART A: RACI CHART
Key Steps | Date | Date | A | B | C | D | PC | FC | DSJ
Develop and share a plan to increase full, active , conscious participation
Establish / share the elements of FACP (full active conscious participation)
Develop: educate parishioners on Liturgy and participation elements
Enable: create an environment conducive to FACP
Remind parioshioners; solicit feedback; monitor rating annually.
Dates and responsibilities to be determined by each parish.
| PC | Pastoral Council (Parish Council)
| FC | Finance Committee
| DSJ | Chancery (will need to be more specific based on needs)

## Witness Plan
Pillar Mission: All parishioners to encounter Jesus Christ by serving those in need.
MACRO STEP(S) | 1. Develop a highly effective Social Ministries leadership team; | 3 | Establish a process to solicit feedback for each
| 2. Develop a comprehensive Social Ministries plan; |  | service encounter program / event.
GOAL
Double the # of encounter options by June 2017; double again by June 2019.
Program | Key Steps |  | Comments
| Hire / appoint Social Ministries leader. Form strong SM team. |  | Share resource with neighboring parish?
Encounter | Plan: develop and communicate a Social Ministries plan |  | SMART goals; roles, required resources; funding
Opportunities | Assess: the effectiveness and reach of current encounter events |  | See sample matrix
| Scope: create opportunities to maximize parishioner service |  | Tons of programs out there. Don't reinvent the wheel
| Communicate: encounter opportunities to all parishioners |  | Communication is key!
GOAL
70% of parishioners in at least 1 annual service encounter by June '17; 90% by June '19
Program | Key Steps |  | Comments
| Communicate: Social Ministries plan and parishioner service goals |  | Communication is key!
Encounter | Inform: Catholic Social Teachings and extreme DSJ needs |  | Homilies; bulletins, classes, etc.
Experiences | Inspire: Share our call to serve. |  | Leverage scriptures and especially Pope Francis.
| Invite: Personally invite parishioners to encounter opportunities |  | Clergy invites "wave I"; parishioners invite "wave II"
| Monitor: gather feedback on encounters. Share testimonials. |  | All testimonials will be powerful, especially videos!
GOAL
2% average stewardship of time, talent and treasure by June '17. 3% by June '19.
Program | Key Steps |  | Comments
| Form a Stewardship Committee. Develop a stewardship plan. |  | Stewardship will likely lag Word, Witness by a year.
Increase | Communicate: Teach stewardship; inform of TTT needs and causes. |  | Homilies; bulletins, FF programs, classes, etc.
Stewardship | Communicate: current and desired results. Set personal goals. |  | May take 2-3 years to get there.
(Time, Talent, $$$) | Monitor: be transparent; report results regularly. |  | Communication is key!
| Record / share testimonials (those serving; those being served) |  | All testimonials will be powerful, especially videos!
Notes: | Each "Key Action" will need a detailed "action plan" with specifc steps. |  | Note: All SMART goals listed are for
| Action Plans would typically be prepared by the person "Responsible" |  | illustrative purposes. Each parish to set
| for the execution of the plan. Each action plan could have its own RACI. |  | their own specific SMART goals.

## Witness RACI
|  |  | R | Responsible for execution.
Pillar Mission: All parionsers to encounter Jesus Christ by serving those in need. |  |  | A | Accountable that action gets completed
|  |  | C | Consultation required before execution
|  |  | I | Inform, but advance approval not required.
Targeted
| Start | End | RACI CHART
Key Action | Date | Date | A | B | C | D | PC | FC | DSJ
Hire / appoint Social Ministries leader. Form strong SM team.
Plan: develop and communicate a Social Ministries plan
Assess: the effectiveness and reach of current encounter events
Scope: create opportunities to maximize parishioner service
Communicate: encounter opportunities to all parishioners
| Start | End | RACI CHART
Key Action | Date | Date | A | B | C | D | PC | FC | DSJ
Communicate: Social Ministries plan and parishioner service goals
Inform: Catholic Social Teachings and extreme DSJ needs
Inspire: Share our call to serve.
Invite: Personally invite parishioners to encounter opportunities
Monitor: gather feedback on encounters. Share testimonials.
| Start | End | RACI CHART
Key Action | Date | Date | A | B | C | D | PC | FC | DSJ
Form a Stewardship Committee. Develop a stewardship plan.
Communicate: Teach stewardship; inform of TTT needs and causes.
Communicate: current and desired results. Set personal goals.
Monitor: be transparent; report results regularly.
Record / share testimonials (those serving; those being served)
Dates and responsibilities to be determined by each parish.
| PC | Pastoral Council (Parish Council)
| FC | Finance Committee
| DSJ | Chancery (will need to be more specific based on needs)

## High Level Timeline
PILLAR | Major Goal and Program | Nov | Dec | Q1 '16 | Q2 '16 | Q3 '16 | Q4 '16 | Q1 '17 | Principal Owner
Lead | Leadership Plan / Teambuilding | Plan |  |  |  |  | Update |  | Pastor / Pastoral Council
| Communicate / Validate the Vision, Mission & Plan with Parishioners |  |  | Plan |  |  |  | Update | Pastor
| Strengthen Personal Prayer Life - Teach / Enable Parishioners |  |  | Pray |  |  |  |  | Pastor / DRE
Word | Improve Faith Formation - Strategic Plan |  |  | Plan | Implement |  |  | Attend | DRE
| High Quality FF Leaders - Recruiting / Training Plan |  |  | Plan | Implement |  |  |  | DRE
| Improve Homilies - Clergy Coaching / Training |  |  | Plan | Implement |  |  |  | Chancery + Lots of clergy time / energy.
Worship | Improve Music - Strategic Plan |  |  |  | Plan | Implement |  |  | Director of Music
| Active Participation - Parishioner Education / Expectation |  |  |  | Participate |  |  |  | Director of Liturgy
| Increase Encounter Opportunities | Homelessness |  | Plan |  |  |  |  | Chancery / Social Ministry Leader
Witness | Increase Encounter Experiences | Homelessness |  |  |  | Serve |  |  | Chancery / Social Ministry Leader
| Increase Stewardship (Time, Talent, Treasure) | [5 empty] | Pledge |  | Pastor / Pastoral Council
| Pastor / Pastoral Team led initiative / activity. |  |  | Note: A purpose of this template is to show
that no one person / team should be overly
| Activity requiring significant parishioner participation. |  |  | burdened despite the fact that multiple goals
will be tackled simultaneously.

## Master Plan
# | Staging / sequencing of when parishioners will be asked to act (1 ask per quarter)
PILLAR | PROGRAM | ACTIONS | Nov | Dec | Q1 '16 | Q2 '16 | Q3 '16 | Q4 '16 | Q1 '17 | Q2 '17 | Q3 '17 | Comments
L |  | Develop / Share Compelling Vision/Mission; Support with Compelling Data | Pastoral Team | [8 empty] | Distinguish vision from mission.
E | Leadership | Form / Empower Strong Leadership Teams for Each Pillar | Pastoral Team | [8 empty] | Not the PC; rather unique teams. Recruit!
A | Actions | Document the Parish Evangelization Plan (Goals, Roles, Budgets, etc) | Pastoral Team | [8 empty] | Critical step. Do not short cut this step.
D | Plans | Communicate / Validate the Vision, Mission & Plan with Parishioners |  |  | Pastor | [6 empty] | Formal commincation plan (10x).
|  | Finalize & Launch Plan; Establish Periodic Tracking Measures |  |  |  | Parish Dashboard to track and report Parish goals and progress | [5 empty] | Need a dashboard to hold people accountable.
|  | Establish / share homily standards |  | Chancery | [7 empty] | Chancery will likely own this step
W | Improve | Develop: clergy training, videotaping, coaching, peer review |  |  | Chancery + a lot of clergy time and energy | [6 empty] | Clergy need / should buy in. DSJ funding ???
| Homilies | Communicate: share homily standards and goals with parishioners |  |  |  | Pastor | [5 empty] | Communication / education is key!
O |  | Understand parishioners' needs / issues. Allocate proper prep time. |  |  |  |  | Clergy / Pastoral Council / Preaching Board |  |  |  |  | Ask / know parishioners need / issues.
|  | Solicit feedback weekly; monitor satisfaction rating semi-annually. | [6 empty] | Parish Dashboard |  |  | Need embedded on website; ask for feedback
R |  | Secure / hire a strong director of music; establish a music board. |  |  |  | Pastor | [5 empty] | Share resource with another parish?
| Improve | Document a music improvement plan. Consider parishioner input. |  |  |  |  | Music Dir |  |  |  |  | Make parishioners part of the process.
S | Music | Communicate: share music plans and goals with parishioners |  |  |  |  | Music Dir |  |  |  |  | Communication / education is key!
|  | Develop: choirs, musicians, and parishioners. | [5 empty] | Ongoing training / development |  |  |  | Will likely require funding. Budget this.
H |  | Solicit feedback weekly; monitor satisfaction rating semi-annually. | [6 empty] | Parish Dashboard |  |  | Need embedded on website; ask for feedback
|  | Develop and share a plan to increase full, active , conscious participation |  |  | Lit Dir | [6 empty] | Perhaps DSJ plan; communicated locally
I | Full, Conscious | Establish / share the elements of FACP (full active conscious participation) |  |  |  | Lit Dir | [5 empty] | Ideal if consistent across DSJ
| Active | Develop: educate parishioners on Liturgy and participation elements |  |  |  | 2 - Active | [5 empty] | Don't assume parishioners understand the Liturgy
P | Participation | Enable: create an environment conducive to FACP |  |  |  |  | Lit Comm |  |  |  |  | Environment minsters are key to FACP.
|  | Remind parioshioners; solicit feedback; monitor rating annually. | [6 empty] | Parish Dashboard |  |  | Need embedded on website; ask for feedback
|  | Develop: a plan to assess / strengthen the prayer lives of all parishioners |  |  | DRE | [6 empty] | Each parishioner to assess where they are at
|  | Communicate: expectations for / benefits of daily prayer |  |  | 1 - Pray | [6 empty] | Communication / education is key!
W | Personal | Develop: teach people how to pray |  |  |  | Clergy | [5 empty] | Communication / education is key!
| Prayer Life | Enable: make it easy for people to pray with books, websites |  |  |  | DRE | [5 empty] | No excuses. Make it super easy for them.
|  | Monitor: Solicit feedback from each FF program. | [5 empty] | Formal evaluation process |  |  |  | Need embedded on website; ask for feedback
O |  | Assess: the effectiveness and reach of current FF programs / events. |  |  |  | DRE | [5 empty] | Informally assess where FF is at
| Increase # of | Scope: Identify programs to ensure there is something for all parishioners |  |  |  |  | DRE |  |  |  |  | See sample matrix
| High Quality | Communicate: to parishioners the goal to "Invest in Their Faith" |  |  |  |  | Pastor |  |  |  |  | Communication / education is key!
R | FF Programs | Personally invite parishioners to participate in 1 FF event per quarter. | [6 empty] | 5 - Learn |  |  | Broad invitations won't be as effective
|  | Monitor: Solicit feedback from each FF program. | [5 empty] | Formal evaluation process |  |  |  | Need embedded on website; ask for feedback
|  | Assess: the role and effectiveness of each current FF leader |  |  | DRE | [6 empty] | Not punitive; basis for future training.
D | Increase # of | Develop: a recruitment and development plan to add skilled FF leaders. |  |  |  | Ongoing recruiting efforts by DRE and other FF Leaders | [5 empty] | Formally document and track progress.
| High Quality | Communicate: expectation that all adults and parents are FF leaders |  |  |  |  | Pastor |  |  |  |  | Enable parents to more comfortable
| FF Leaders | Develop: provide FF leaders and parents with proper training. |  |  |  |  | Ongoing training and development |  |  |  |  | Have to make it EASY for parents.
|  | Assess: Solicit feedback on FF leaders; train / coach as needed | [6 empty] | Parish Dashboard |  |  | Need embedded on website; ask for feedback
|  | Hire / appoint Social Ministries leader. Form strong SM team. |  |  | SM Dir | [6 empty] | Shared resource or events with another parish?
W | Increase | Plan: develop and communicate a Social Ministries plan |  |  | SM Dir | [6 empty] | Shared resource or events with another parish?
| Encounter | Assess: the effectiveness and reach of current encounter events |  |  | SM Dir | [6 empty] | Maintain, add or discontinue events.
I | Opportunities | Scope: create opportunities to maximize parishioner service |  |  |  | SM Comm | [5 empty] | Make sure there is something for everyone.
|  | Communicate: encounter opportunities to all parishioners | 0 - Homelessness |  |  | SM Comm | [5 empty] | Communicate broadly follwed by personal invites
T |  | Communicate: Social Ministries plan and parishioner service goals |  |  |  | SM Comm | [5 empty] | Strong team needed for increase in volunteers
| Increase | Inform: Catholic Social Teachings and extreme DSJ needs |  |  |  |  | Pastor |  |  |  |  | Must be informed before they are inspired.
N | Encounter | Inspire: Share our call to serve. |  |  |  |  | Pastor |  |  |  |  | Must be informed before they are inspired.
| Experiences | Invite: Personally invite parishioners to encounter opportunities |  |  |  |  | 3 - Serve |  |  |  |  | All disciples / leaders to invite others to serve
E |  | Monitor: gather feedback on encounters. Share testimonials. | [6 empty] | Weekly testimonial |  |  | Testimonials are powerful, especially videos!
|  | Form a Stewardship Committee. Develop a stewardship plan. |  |  |  | Stewardship Comm | [5 empty] | Extreme need for SMART goals.
S | Increase | Communicate: Teach stewardship; inform of TTT needs and causes. | [5 empty] | Pastor |  |  |  | Need development / campaign team engaged
| Stewardship | Communicate: current and desired results. Set personal goals. | [5 empty] | 4 - Steward |  |  |  | Set stewardship goals (TTT); repeat annually.
S | (Time, Talent, $$$) | Monitor: be transparent; report results regularly. | [6 empty] | Parish Dashboard |  |  | Share / celebrate interim milestones.
|  | Record / share testimonials (those serving; those being served) | [6 empty] | Weekly testimonial |  |  | Testimonials are powerful, especially videos!

## Changing the World
Changing the World: Parish "X" Potential
Goals:
1. Double the # of disciples every 5 years.
2. Each disciple changes 4 lives each year.
Year | # of Disciples | Lives Changed
2015 |  | 0
2020 | 0 | 0
2025 | 0 | 0
2030 | 0 | 0
2035 | 0 | 0
2040 | 0 | 0
Total Lives Changed |  | 0
A Disciple:
One who believes, lives and spreads the teachings of Jesus Christ
Input estimated # of disciples here. The rest is automatically calculated.
Maybe start with 5% of your parishioners?
Possible definition. Feel free to add your own. Should be a high standard!

## Formation Coverage
FAITH FORMATION PROGRAM | Seniors | Empty Nesters | Parents w/ School Aged kids | Young Adults | High School / Jr High | Pre-K thru Middle school | New Parishioners | Inactive Parishioners | Program Participant Rating
A
B
C
D
E
F
G
H
I
J
K
L
Self-Assessment of program by Faith Formation leadership team:
Program / activity considered to be of high value and s/b continued.
Program / activity considered to be of average value and s/b upgraded.
Program / activity considered to be of low value and s/n/b continued.

## Encounter Coverage
Encounter Program | Seniors | Empty Nesters | Parents w/ School Aged kids | Young Adults | High School / Jr High | Pre-K thru Middle school | New Parishioners | Inactive Parishioners | Program Participant Rating
A
B
C
D
E
F
G
H
I
J
K
L
Self-Assessment of program by Witness / Social Ministry leadership team:
Program / activity considered to be of high value and s/b continued.
Program / activity considered to be of average value and s/b upgraded.
Program / activity considered to be of low value and s/n/b continued.